## Sheet1
ACTION PLAN
NO | ACTION STEP | RESPONSIBLE | START DATE | DUE DATE | RESOURCE | Status | COMMENTS
1 | Implement a new Backup System for all critical systmes | Kwesi, David, Hilary | 13/01/2025 | 27/01/2025 | Additional Server with moderate specifications
2 | Develop USSD platform for internal and external to increase in-house software development. | Kwesi, David | 2025-03-18
3 | Expand the system monitoring and alert platforms | Kwesi, Hilary | 2025-03-14 |  | will be deployed on the same Tech Team server
4 | Implement a new Business Intelligent (BI) tool | Hilary | 2025-04-08 | 31/01/2025 |  |  | We are going to use Metbase. Installation completed, we just need to design the reports
5 | Acquire new sever for development, staging, testing and monitoring | Kwesi, Sam | 2025-03-13 | 2025-03-13 | Server with moderate specifications
6 | TNM Diameter | Hilary | 2024-07-04 | 31/01/2025 |  |  | Waiting for Henrie to whitelist our peer IPs at the application level.
7 | SMS Gateway Development(FCB Group, Bulk Tool & Click Mobile SMS Gateway) | All | 17/01/2025 | 17/01/2026 |  |  | Strategy shared for review.
8 | Conduct penetration testing, run security test a with consultant | Hilary, Kwesi | 2025-03-25 | 2025-03-29
9 | Attend IT related conferences | All
10 | Adopt additional Open Source tools for operations | All | 2025-03-25 | 2025-03-29